## Main
Scrum Project
Product | SmartRegression AI
Active versions | MVP v1.0 planned
Team |  |  | Product Owner | Jan Samuelsson
Scrum Master | Nguyen Tan Huy |  | Other Stakeholders | Jan Samuelsson - Project Mentor
Developers | Nguyen Tan Huy |  |  | Developers and QA Engineers | Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
| Do Ha An |  |  |  | 1 | Week 1 | Week 3 | Planned |  |  | Research foundation + technical spike
| Pham Phan Hoang Huy |  |  |  | 2 | Week 4 | Week 6 | Planned | 232 |  | Proposed plan; see Sprint 2 Reports.
| Tran Hung Khanh |  |  |  | 3 | Week 7 | Week 9 | Planned |  |  | LLM-assisted test selection + fallback + pilot execution
| Dang Dai Viet |  |  |  | 4 | Week 10 | Week 12 | Planned |  |  | CI/CD + baselines + evaluation + finalization
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status |  | Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
SR-AI-01 | SmartRegression AI MVP | 2026-08-23 | 2026-12-13 | In planning |  | 1 |  |  | Planned | 194 |  | Research foundation and technical spike
[6 empty] | 2 |  |  | Planned | 232 |  | Proposed 232 task hours; reserve 32h; resource need 264h. Actual capacity pending. PostgreSQL accepted by user; see Sprint 2 Reports.
[6 empty] | 3 | 1900-01-02 | 1900-01-13 | Planned |  |  | LLM-assisted selection and dataset preparation
[6 empty] | 4 | 1900-01-16 | 1900-01-27 | Planned |  |  | Full evaluation and project finalization
[7 empty] | 1900-01-30 | 1900-02-10
Formulas:
End = [Status, row above]+3
Status = [End]+11

## Product Backlog
Product Backlog aligned to Proposal v1.4. Planning estimates are Scrum estimates; research outcomes are not pre-claimed.
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Connect authorized GitHub repository | Maintainer | connect an authorized GitHub repository | the system can access the selected project safely | Accept valid authorized repository; show identity/status; reject unauthorized access | FR-01 | 1 | Proposed | Feature | SmartRegression AI | 1 | 15 | Nguyen Tan Huy |  |  | Initial estimate
PB02 | Configure testing environment | Maintainer | configure one supported test framework, locations, command, timeout and resource limits | analysis can be executed under controlled rules | Validate required settings; reject invalid command or non-positive limits; persist configuration | FR-02 | 1 | Proposed | Feature | SmartRegression AI | 1 | 15 | Tran Hung Khanh |  |  | Initial estimate
PB03 | Select and freeze change range | Developer | select two commits or a pull request | the exact base and target SHAs are fixed for the run | Resolve base/target SHAs; show changed files; freeze SHAs; new PR head creates a separate run | FR-03 | 1 | Proposed | Feature | SmartRegression AI | 1 | 20 | Do Ha An |  |  | Initial estimate Sprint 2 proposed: 2.15 snapshot prerequisite. PB scope/estimate retained; task hours differ.
PB04 | Start and monitor analysis | Developer | start an analysis run | I can track the run from queue to terminal status | Create run ID; show stage/timestamps/status; retain actionable failure reason; prevent duplicate integration jobs | FR-04 | 1 | Proposed | Feature | SmartRegression AI | 1 | 15 | Nguyen Tan Huy |  |  | Initial estimate Sprint 2 proposed: 2.13/2.14; 2.20 foundation support. PB scope/estimate retained; task hours differ.
PB05 | Review code changes | Developer | review changed files/functions/classes/modules and diffs | I can understand what changed | Display diffs and source locations resolving at the analyzed version | FR-05 | 1 | Proposed | Feature | SmartRegression AI | 2 | 25 | Do Ha An |  |  | Initial estimate Sprint 2 proposed: 2.01/2.02; 2.14/2.15/2.18 support. PB scope/estimate retained; task hours differ.
PB06 | Compute potential impact | Developer | see directly and indirectly affected components | I can identify possible impact areas | Compute supported dependency paths; distinguish changed vs potentially affected components; disclose unsupported cases | FR-06 | 1 | Proposed | Feature | SmartRegression AI | 2 | 35 | Pham Phan Hoang Huy |  |  | Initial estimate Sprint 2 proposed: 2.03–2.05; 2.14/2.16/2.17/2.20 support. PB scope/estimate retained; task hours differ.
PB07 | Inspect impact evidence | Developer | inspect evidence behind impact explanations | I can verify the analysis | Link source locations, commit references and dependency evidence; mark invalid references unverified | FR-07 | 1 | Proposed | Feature | SmartRegression AI | 2 | 25 | Pham Phan Hoang Huy |  |  | Refine in Sprint 2 Sprint 2 proposed: 2.06; 2.14/2.17/2.18 support. PB scope/estimate retained; task hours differ.
PB08 | Find review starting points | Developer | receive ordered review starting points | I know where to begin manual review | Order changed executable, direct dependents, indirect dependents; stable tie-breaking; no calibrated fault-probability claim | FR-08 | 2 | Proposed | Feature | SmartRegression AI | 2 | 20 | Dang Dai Viet |  |  | Refine in Sprint 2 Sprint 2 proposed: 2.07. PB scope/estimate retained; task hours differ.
PB09 | Discover existing target tests | QA Engineer | view the existing target-version tests | only real existing tests enter the selection inventory | Stable test identifiers and source locations; distinguish empty inventory from discovery failure; record adapter/version | FR-09 | 1 | Proposed | Feature | SmartRegression AI | 2 | 25 | Tran Hung Khanh |  |  | Refine in Sprint 2 Sprint 2 proposed: 2.08/2.09; 2.14/2.16/2.17/2.20 support. PB scope/estimate retained; task hours differ.
PB10 | Generate and validate selection manifest | QA Engineer | receive a validated test-selection manifest | only valid existing tests can be dispatched | Target SHA; selected/not-selected groups; counts; reasons; fallback mode; groups partition inventory; no invented IDs | FR-10 | 1 | Proposed | Feature | SmartRegression AI | 3 | 30 | Tran Hung Khanh |  |  | Refine in Sprint 3
PB11 | Explain test-selection reasons | QA Engineer | inspect reasons for selected and not-selected tests | I can verify each decision | Provide source evidence/dependency path/rule per decision or group; never claim not-selected proves no regression detection | FR-11 | 1 | Proposed | Feature | SmartRegression AI | 3 | 30 | Pham Phan Hoang Huy |  |  | Refine in Sprint 3
PB12 | Apply fallback policy | QA Engineer | receive a conservative fallback when analysis is incomplete | test-reduction risk is controlled | Record trigger and final mode; support dependency+modified set, full-suite fallback, or explicit stop according to proposal rules | FR-12 | 1 | Proposed | Safety | SmartRegression AI | 3 | 30 | Tran Hung Khanh |  |  | Refine in Sprint 3
PB13 | Execute selected or full tests | QA Engineer | run the recommended set or full suite at the frozen target SHA | I can obtain controlled regression results | Runner receives frozen SHA and validated manifest; show actual execution mode and status | FR-13 | 1 | Proposed | Feature | SmartRegression AI | 3 | 30 | Tran Hung Khanh |  |  | Rule to be confirmed
PB14 | Inspect test results | QA Engineer | inspect per-test outcomes and logs | I can distinguish failure types and skipped tests | Show pass/fail/runner-skipped, time and logs; distinguish not-selected from runner-skipped; classify build/assertion/timeout/infrastructure errors | FR-14 | 1 | Proposed | Feature | SmartRegression AI | 3 | 30 | Tran Hung Khanh |  |  | Refine in Sprint 4
PB15 | Browse analysis history | Developer | find previous runs by repository, commit or status | I can reopen an analysis consistently | Reopen original versions, configuration, impact report, selection and execution results | FR-15 | 2 | Proposed | Feature | SmartRegression AI | 4 | 20 | Dang Dai Viet |  |  | Refine in Sprint 3
PB16 | View and export reports | Developer | view a run dashboard and export results | I can review and share evidence-backed results | HTML + JSON; include changes, impacts, evidence, selected/not-selected tests, outcomes, timings, fallback, LLM usage/cost; missing values = N/A | FR-16 | 2 | Proposed | Feature | SmartRegression AI | 4 | 35 | Dang Dai Viet |  |  | Platform to be confirmed
PB17 | Integrate one CI/CD platform | DevOps Engineer | trigger analysis from commit/PR events | the workflow can run experimentally in CI/CD | One platform; return status/outcome/report links; duplicate events idempotent; failures never become passing; full-suite fallback explicitly marked | FR-17 | 2 | Proposed | Integration | SmartRegression AI | 4 | 30 | Tran Hung Khanh |  |  | Initial estimate
PB18 | Run predefined evaluation methods | Researcher / Evaluator | run predefined datasets and supported methods | I can compare the proposed method with baselines | Compare full suite, dependency-based selection, LLM-based selection and SmartRegression AI; N/A for missing labels/zero denominators | FR-18 | 1 | Proposed | Research | SmartRegression AI | 4 | 35 | Dang Dai Viet
PB19 | Build RAG project index | Researcher | index source code, tests and documentation | project-specific context can be retrieved for LLM analysis | Index by repository and commit; preserve path/revision metadata; exclude secrets and evaluation labels | Design: RAG | 1 | Proposed | Research | SmartRegression AI | 2 | 35 | Pham Phan Hoang Huy |  |  | Sprint 2 proposed: 2.10; 2.14/2.15/2.20 support. PB scope/estimate retained; task hours differ.
PB20 | Retrieve change-relevant context | System | retrieve source/tests/docs related to changed and candidate components | the LLM receives focused project context | Queries derived from diff/candidates; ranked results with metadata; record insufficient retrieval | Design: RAG | 1 | Proposed | Feature | SmartRegression AI | 2 | 30 | Pham Phan Hoang Huy |  |  | Sprint 2 proposed: 2.11/2.12; 2.14/2.17/2.20 support. PB scope/estimate retained; task hours differ.
PB21 | Validate LLM output | System | validate LLM proposals before selection/execution | LLM output cannot bypass system safety rules | Validate schema, inventory membership and commit-linked evidence; never interpret LLM output as executable shell commands | Design: LLM | 1 | Proposed | Safety | SmartRegression AI | 3 | 30 | Pham Phan Hoang Huy
PB22 | Implement selection policy | System | combine dependency-selected, modified and valid LLM-added tests | selection is conservative and reproducible | S=(D∪M∪L)∩T; LLM may add but not remove D/M; persist T\S, evidence and policy version | Design: Selection Policy | 1 | Proposed | Research | SmartRegression AI | 3 | 25 | Tran Hung Khanh |  |  | Sprint 2 proposed: 2.16 prepares mapping only; Sprint 3 assignment retained. PB scope/estimate retained; task hours differ.
PB23 | Prepare reproducible evaluation dataset | Researcher | prepare repository versions, commit pairs, labels and known defects | evaluation can be repeated and audited | Target ≥2 repositories, ≥30 commit pairs, ≥15 verified fault-bearing cases; separate real and mutation faults; document limitations | Objective 3 | 1 | Proposed | Research | SmartRegression AI | 1 | 30 | Dang Dai Viet
PB24 | Evaluate metrics and baselines | Researcher | calculate defined research metrics | I can judge effectiveness and trade-offs | Impact Precision/Recall; Evidence Accuracy; Test Reduction Rate; Fault Detection Retention; Missed Fault Rate; E2E Time Reduction; LLM Cost/Token Usage; Fallback Rate | Objective 3 | 1 | Proposed | Research | SmartRegression AI | 4 | 40 | Nguyen Tan Huy
Note on M7: Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.
Note on N7: Just rough numbers, 5,10,15,20 etc. Not 7, 13, 21 etc.

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.01 | PB23 | Define research questions, baselines and metric formulas | Nguyen Tan Huy | Not started | 10 | 0 | 10 | 0
1.02 | PB23 | Define repository screening and evaluation criteria | Dang Dai Viet | Not started | 8 | 0 | 8 | 0
1.03 | PB01 | Select primary and backup repositories for the technical spike | Dang Dai Viet | Not started | 8 | 0 | 8 | 0
1.04 | PB01 | Prototype authorized GitHub repository connection and access validation | Nguyen Tan Huy | Not started | 12 | 0 | 12 | 0
1.05 | PB02 | Define supported test framework configuration and execution constraints | Tran Hung Khanh | Not started | 8 | 0 | 8 | 0
1.06 | PB03 | Define base/target revision and PR SHA-freezing rules | Do Ha An | Not started | 8 | 0 | 8 | 0
1.07 | PB03 | Prototype Git diff extraction and changed-file metadata | Do Ha An | Not started | 14 | 0 | 14 | 0
1.08 | PB04 | Prototype analysis run ID/status lifecycle and failure states | Nguyen Tan Huy | Not started | 8 | 0 | 8 | 0
1.09 | PB19 | Define RAG indexing scope, metadata and secret-exclusion rules | Pham Phan Hoang Huy | Not started | 10 | 0 | 10 | 0
1.10 | PB22 | Define selection/fallback policy and safety boundaries | Tran Hung Khanh | Not started | 10 | 0 | 10 | 0
1.11 | PB24 | Define evaluation protocol and reporting template | Nguyen Tan Huy | Not started | 8 | 0 | 8 | 0
1.12 | PB23 | Document technical-spike findings and Sprint 1 review/demo | Nguyen Tan Huy | Not started | 8 | 0 | 8 | 0
|  |  |  | Total | 112 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Tan Huy | [16 empty] | 0
[8 empty] | Do Ha An | [16 empty] | 0
[8 empty] | Pham Phan Hoang Huy | [16 empty] | 0
[8 empty] | Tran Hung Khanh | [16 empty] | 0
[8 empty] | Dang Dai Viet | [16 empty] | 0
0
Update actual worked hours per team member each day. Keep effort logs separate from planned task estimates.
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Sprint 1 Reports & Dashboards
Sprint goal: Research foundation + technical spike
Record burn-down/burn-up, sprint review evidence, achieved acceptance checks and key decisions. | Burn up Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2.01 | PB05 | Identify changed files, functions, classes and modules | Do Ha An | Not started | 20 | 0 | 20 | 0
2.02 | PB05 | Validate changed-component locations independently | Dang Dai Viet | Not started | 8 | 0 | 8 | 0
2.03 | PB06 | Build supported static dependency graph | Pham Phan Hoang Huy | Not started | 16 | 0 | 16 | 0
2.04 | PB06 | Traverse reverse-reachable potential impact and cycles | Pham Phan Hoang Huy | Not started | 12 | 0 | 12 | 0
2.05 | PB06 | Persist dependency paths and source evidence | Nguyen Tan Huy | Not started | 8 | 0 | 8 | 0
2.06 | PB07 | Explain potential impact and inspect individual evidence items | Nguyen Tan Huy | Not started | 12 | 0 | 12 | 0
2.07 | PB08 | Order review starting points deterministically | Dang Dai Viet | Not started | 8 | 0 | 8 | 0
2.08 | PB09 | Discover existing target tests in isolation | Tran Hung Khanh | Not started | 12 | 0 | 12 | 0
2.09 | PB09 | Distinguish empty, incomplete and failed discovery | Tran Hung Khanh | Not started | 6 | 0 | 6 | 0
2.10 | PB19 | Index permitted source, tests and documentation by snapshot | Pham Phan Hoang Huy | Not started | 16 | 0 | 16 | 0
2.11 | PB20 | Retrieve context from diff and candidate components | Pham Phan Hoang Huy | Not started | 12 | 0 | 12 | 0
2.12 | PB20 | Rank, deduplicate and verify retrieval metadata | Dang Dai Viet | Not started | 8 | 0 | 8 | 0
2.13 | PB04 | Integrate workflow incrementally and prepare Sprint 2 demo | Nguyen Tan Huy | Not started | 12 | 0 | 12 | 0
2.14 | PB04 | Define integration contracts and stage reports | Nguyen Tan Huy | Not started | 12 | 0 | 12 | 0
2.15 | PB03 | Prepare authorized immutable snapshots | Do Ha An | Not started | 10 | 0 | 10 | 0
2.16 | PB06/PB09 | Map components to existing target test IDs | Tran Hung Khanh | Not started | 8 | 0 | 8 | 0
2.17 | PB06/07/09/20 | Propagate analysis coverage and limitations | Do Ha An | Not started | 10 | 0 | 10 | 0
2.18 | PB05/PB07 | Integrate real-report inspection UI | Dang Dai Viet | Not started | 10 | 0 | 10 | 0
2.19 | Integration | Verify cross-module integrity and failure regressions | Tran Hung Khanh | Not started | 8 | 0 | 8 | 0
2.20 | PB04/06/09/19/20 | Establish PostgreSQL persistence foundation | Nguyen Tan Huy | Not started | 24 | 0 | 24 | 0
|  |  |  | Total | 232 | 0 | 232 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 232
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Tan Huy | [16 empty] | 0
[8 empty] | Do Ha An | [16 empty] | 0
[8 empty] | Pham Phan Hoang Huy | [16 empty] | 0
[8 empty] | Tran Hung Khanh | [16 empty] | 0
[8 empty] | Dang Dai Viet | [16 empty] | 0
0
Update actual worked hours per team member each day. Keep effort logs separate from planned task estimates.
Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria) | Sprint 2 task briefs (proposed scope and acceptance criteria)
All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit. | All tasks below are planned, not accepted results. Original IDs/PB links are retained; wording makes identity, isolation and limitations explicit.
2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions | 2.01 Changed-component records at base/target revisions
Dependencies | Dependencies | 2.14 contract; 2.15 snapshot | 2.14 contract; 2.15 snapshot | 2.14 contract; 2.15 snapshot | 2.14 contract; 2.15 snapshot | 2.14 contract; 2.15 snapshot | 2.14 contract; 2.15 snapshot | 2.14 contract; 2.15 snapshot | 2.14 contract; 2.15 snapshot
Acceptance criteria | Acceptance criteria | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact. | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact. | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact. | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact. | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact. | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact. | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact. | Handle add/modify/delete/rename with previous path; distinguish file/module/class/function granularity. Every location resolves at its declared base or target commit. Unsupported syntax is partial, not no-impact.
Verification planned | Verification planned | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation. | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation. | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation. | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation. | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation. | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation. | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation. | Fixtures with independently expected changes and immutable Git blobs; include deletion, rename and dirty-tree isolation.
Traceability / review | Traceability / review | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h. | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h. | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h. | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h. | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h. | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h. | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h. | PB05. Reviewer proposed: pending. Allocation: Do Ha An 20h.
2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record | 2.02 Reviewed expected locations and mismatch record
Dependencies | Dependencies | 2.01 output; 2.14 contract | 2.01 output; 2.14 contract | 2.01 output; 2.14 contract | 2.01 output; 2.14 contract | 2.01 output; 2.14 contract | 2.01 output; 2.14 contract | 2.01 output; 2.14 contract | 2.01 output; 2.14 contract
Acceptance criteria | Acceptance criteria | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth. | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth. | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth. | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth. | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth. | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth. | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth. | Compare output with independently prepared expected components and source ranges. Reject wrong commit/path/span; record unresolved labels and disagreements. Dependency reachability is not ground truth.
Verification planned | Verification planned | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence. | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence. | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence. | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence. | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence. | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence. | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence. | Positive and wrong-location cases; retain fixture revisions, expected records and mismatch evidence.
Traceability / review | Traceability / review | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB05. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h.
2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges | 2.03 Snapshot-scoped components and supported dependency edges
Dependencies | Dependencies | 2.01; 2.14; 2.15 | 2.01; 2.14; 2.15 | 2.01; 2.14; 2.15 | 2.01; 2.14; 2.15 | 2.01; 2.14; 2.15 | 2.01; 2.14; 2.15 | 2.01; 2.14; 2.15 | 2.01; 2.14; 2.15
Acceptance criteria | Acceptance criteria | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved. | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved. | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved. | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved. | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved. | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved. | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved. | Document supported import/reference semantics and edge direction. Every endpoint belongs to the same repository/snapshot. Relative, star and dynamic imports are either supported with evidence or explicitly unresolved.
Verification planned | Verification planned | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints. | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints. | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints. | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints. | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints. | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints. | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints. | Independent expected-edge fixtures for supported/unsupported imports and wrong-snapshot endpoints.
Traceability / review | Traceability / review | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 16h.
2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths | 2.04 Direct/indirect potential-impact candidates and paths
Dependencies | Dependencies | 2.03; 2.14 | 2.03; 2.14 | 2.03; 2.14 | 2.03; 2.14 | 2.03; 2.14 | 2.03; 2.14 | 2.03; 2.14 | 2.03; 2.14
Acceptance criteria | Acceptance criteria | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change. | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change. | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change. | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change. | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change. | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change. | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change. | Traverse reverse dependency direction from changed components; distinguish changed, direct and indirect candidates. Cycles terminate and paths deduplicate deterministically. Reachability is potential impact, not verified behavioral change.
Verification planned | Verification planned | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths. | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths. | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths. | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths. | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths. | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths. | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths. | Chain, branching, cycle, disconnected and deterministic-repeat fixtures with expected candidates/paths.
Traceability / review | Traceability / review | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB06. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h.
2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity | 2.05 Persisted impact paths and evidence with revision identity
Dependencies | Dependencies | 2.04; 2.14; 2.20 foundation checkpoint | 2.04; 2.14; 2.20 foundation checkpoint | 2.04; 2.14; 2.20 foundation checkpoint | 2.04; 2.14; 2.20 foundation checkpoint | 2.04; 2.14; 2.20 foundation checkpoint | 2.04; 2.14; 2.20 foundation checkpoint | 2.04; 2.14; 2.20 foundation checkpoint | 2.04; 2.14; 2.20 foundation checkpoint
Acceptance criteria | Acceptance criteria | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination. | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination. | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination. | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination. | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination. | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination. | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination. | Round-trip paths/evidence without changing repository/run/commit/path/span identity. Reject cross-snapshot references and surface write/read failures. Own path/evidence persistence logic; reuse 2.20 infrastructure and migration coordination.
Verification planned | Verification planned | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort. | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort. | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort. | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort. | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort. | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort. | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort. | PostgreSQL round-trip, foreign-identity rejection and failure tests; no duplicate infrastructure effort.
Traceability / review | Traceability / review | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h. | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h. | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h. | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h. | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h. | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h. | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h. | PB06. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 8h.
2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view | 2.06 Explanation payload and reusable evidence-item view
Dependencies | Dependencies | 2.04; 2.14; 2.05 for persisted inspection | 2.04; 2.14; 2.05 for persisted inspection | 2.04; 2.14; 2.05 for persisted inspection | 2.04; 2.14; 2.05 for persisted inspection | 2.04; 2.14; 2.05 for persisted inspection | 2.04; 2.14; 2.05 for persisted inspection | 2.04; 2.14; 2.05 for persisted inspection | 2.04; 2.14; 2.05 for persisted inspection
Acceptance criteria | Acceptance criteria | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18. | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18. | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18. | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18. | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18. | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18. | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18. | Explanations reference supported paths and resolve evidence at the declared commit/path/range. Invalid evidence is unverified. H1 owns payload/validation; VI owns the individual evidence component reused by 2.18.
Verification planned | Verification planned | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim. | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim. | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim. | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim. | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim. | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim. | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim. | Payload/component cases for valid, missing and mismatched evidence; no calibrated fault-probability claim.
Traceability / review | Traceability / review | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h. | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h. | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h. | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h. | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h. | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h. | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h. | PB07. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 6h; Dang Dai Viet 6h.
2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points | 2.07 Stable ordered manual-review starting points
Dependencies | Dependencies | 2.01; 2.04; 2.14 | 2.01; 2.04; 2.14 | 2.01; 2.04; 2.14 | 2.01; 2.04; 2.14 | 2.01; 2.04; 2.14 | 2.01; 2.04; 2.14 | 2.01; 2.04; 2.14 | 2.01; 2.04; 2.14
Acceptance criteria | Acceptance criteria | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability. | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability. | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability. | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability. | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability. | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability. | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability. | Order changed executable components, direct dependents and indirect dependents according to the documented rule. Apply stable tie-breaking and deduplication; retain limitations. Ordering does not select tests or estimate fault probability.
Verification planned | Verification planned | Expected ordering for ties, repeated input, duplicates and partial graphs. | Expected ordering for ties, repeated input, duplicates and partial graphs. | Expected ordering for ties, repeated input, duplicates and partial graphs. | Expected ordering for ties, repeated input, duplicates and partial graphs. | Expected ordering for ties, repeated input, duplicates and partial graphs. | Expected ordering for ties, repeated input, duplicates and partial graphs. | Expected ordering for ties, repeated input, duplicates and partial graphs. | Expected ordering for ties, repeated input, duplicates and partial graphs.
Traceability / review | Traceability / review | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB08. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h.
2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance | 2.08 Frozen target-version pytest inventory and provenance
Dependencies | Dependencies | 2.14; 2.15; 2.20 for durable inventory | 2.14; 2.15; 2.20 for durable inventory | 2.14; 2.15; 2.20 for durable inventory | 2.14; 2.15; 2.20 for durable inventory | 2.14; 2.15; 2.20 for durable inventory | 2.14; 2.15; 2.20 for durable inventory | 2.14; 2.15; 2.20 for durable inventory | 2.14; 2.15; 2.20 for durable inventory
Acceptance criteria | Acceptance criteria | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details. | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details. | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details. | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details. | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details. | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details. | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details. | Collect existing target test IDs in an isolated runner; conftest/install hooks never run in API/dashboard or directly on host. IDs bind to repo/run/target and adapter configuration. Preserve time/resource/output limits and failure details.
Verification planned | Verification planned | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation. | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation. | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation. | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation. | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation. | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation. | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation. | Authorized fixture/candidate inventory reproduction; wrong snapshot, timeout and collection-error checks. Reuse persistence foundation.
Traceability / review | Traceability / review | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 12h.
2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states | 2.09 Explicit inventory completeness and failure states
Dependencies | Dependencies | 2.08; 2.14 | 2.08; 2.14 | 2.08; 2.14 | 2.08; 2.14 | 2.08; 2.14 | 2.08; 2.14 | 2.08; 2.14 | 2.08; 2.14
Acceptance criteria | Acceptance criteria | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling. | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling. | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling. | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling. | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling. | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling. | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling. | Successful empty inventory differs from partial collection, timeout and discovery failure. Propagate actionable reasons without treating failure as safe empty selection. Preserve native test IDs and duplicate handling.
Verification planned | Verification planned | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory. | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory. | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory. | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory. | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory. | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory. | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory. | Isolated fixtures for successful empty, collection exception, timeout, partial and duplicate inventory.
Traceability / review | Traceability / review | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h. | PB09. Reviewer proposed: pending. Allocation: Tran Hung Khanh 6h.
2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata | 2.10 Snapshot index, chunk manifest and retrieval metadata
Dependencies | Dependencies | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint | 2.14; 2.15; retrieval decision; 2.20 metadata checkpoint
Acceptance criteria | Acceptance criteria | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks. | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks. | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks. | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks. | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks. | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks. | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks. | Index only permitted source/tests/docs with repo/commit/path/range/content hash and index version. Exclude secrets, fault labels and reference outcomes. Stale/incomplete builds cannot be ready. H2 owns index; KH owns exclusions/leakage checks.
Verification planned | Verification planned | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors. | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors. | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors. | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors. | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors. | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors. | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors. | Manifest/provenance, content-hash and exclusion fixtures. Retrieval backend/embedding decision precedes implementation; PostgreSQL stores metadata, not implicitly vectors.
Traceability / review | Traceability / review | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h. | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h. | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h. | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h. | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h. | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h. | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h. | PB19. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h; Tran Hung Khanh 4h.
2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance | 2.11 Change-relevant retrieved context with provenance
Dependencies | Dependencies | 2.10; 2.01; 2.04; 2.14 | 2.10; 2.01; 2.04; 2.14 | 2.10; 2.01; 2.04; 2.14 | 2.10; 2.01; 2.04; 2.14 | 2.10; 2.01; 2.04; 2.14 | 2.10; 2.01; 2.04; 2.14 | 2.10; 2.01; 2.04; 2.14 | 2.10; 2.01; 2.04; 2.14
Acceptance criteria | Acceptance criteria | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions. | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions. | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions. | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions. | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions. | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions. | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions. | Query only an index matching repository and frozen commit semantics. Return sources and limitations; stale/wrong-repo indexes fail explicitly. Context construction excludes reference outcomes/fault labels and does not execute retrieved instructions.
Verification planned | Verification planned | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata. | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata. | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata. | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata. | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata. | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata. | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata. | Authorized snapshot fixtures for relevant, empty, stale and wrong-repo retrieval; retain query and source metadata.
Traceability / review | Traceability / review | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h. | PB20. Reviewer proposed: pending. Allocation: Pham Phan Hoang Huy 12h.
2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list | 2.12 Deterministic deduplicated and validated context list
Dependencies | Dependencies | 2.11; 2.14 | 2.11; 2.14 | 2.11; 2.14 | 2.11; 2.14 | 2.11; 2.14 | 2.11; 2.14 | 2.11; 2.14 | 2.11; 2.14
Acceptance criteria | Acceptance criteria | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence. | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence. | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence. | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence. | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence. | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence. | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence. | Document ranking/tie-breaking, deduplicate without losing provenance, and validate repo/commit/path/range/hash. Reject invalid references or expose partial results. Ranking scores are not measured accuracy or calibrated confidence.
Verification planned | Verification planned | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases. | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases. | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases. | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases. | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases. | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases. | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases. | Expected rank/dedup cases; mismatched hash/span/revision and partial metadata cases.
Traceability / review | Traceability / review | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h. | PB20. Reviewer proposed: pending. Allocation: Dang Dai Viet 8h.
2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo | 2.13 Shared application workflow, CLI entrypoint and reproducible demo
Dependencies | Dependencies | 2.14 first; integrate stage outputs as available | 2.14 first; integrate stage outputs as available | 2.14 first; integrate stage outputs as available | 2.14 first; integrate stage outputs as available | 2.14 first; integrate stage outputs as available | 2.14 first; integrate stage outputs as available | 2.14 first; integrate stage outputs as available | 2.14 first; integrate stage outputs as available
Acceptance criteria | Acceptance criteria | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases. | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases. | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases. | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases. | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases. | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases. | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases. | Start a thin flow in week 1, integrate stages incrementally, emit honest stage statuses and revision-bound reports. CLI calls application logic; no fabricated selection/execution fields. Own wiring/smoke/demo; 2.19 owns cross-module regression cases.
Verification planned | Verification planned | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced. | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced. | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced. | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced. | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced. | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced. | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced. | Reproduction instructions, CLI smoke artifacts and demo report on authorized fixture/candidate. Human acceptance remains pending until evidenced.
Traceability / review | Traceability / review | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h. | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h. | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h. | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h. | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h. | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h. | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h. | PB04. Reviewer proposed: pending. Allocation: Nguyen Tan Huy 12h.
2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts | 2.14 Reviewed producer/consumer stage contracts
Dependencies | Dependencies | Existing contracts and Sprint 1 decisions; no task prerequisite | Existing contracts and Sprint 1 decisions; no task prerequisite | Existing contracts and Sprint 1 decisions; no task prerequisite | Existing contracts and Sprint 1 decisions; no task prerequisite | Existing contracts and Sprint 1 decisions; no task prerequisite | Existing contracts and Sprint 1 decisions; no task prerequisite | Existing contracts and Sprint 1 decisions; no task prerequisite | Existing contracts and Sprint 1 decisions; no task prerequisite
Acceptance criteria | Acceptance criteria | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation. | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation. | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation. | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation. | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation. | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation. | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation. | Define repo/run/base-target identity, changed/impact/evidence, inventory/retrieval statuses and limitations. Stage reports work without fake selected/skipped decisions. Review compatibility and persistence interface before implementation.
Verification planned | Verification planned | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly. | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly. | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly. | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly. | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly. | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly. | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly. | Contract examples, consumer checks and review record; current AnalysisReport requires selection, so reconcile stage reporting explicitly.
Traceability / review | Traceability / review | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h. | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h. | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h. | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h. | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h. | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h. | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h. | PB04/PB05-09/PB19/PB20. Reviewer proposed: Do Ha An, Dang Dai Viet. Allocation: Nguyen Tan Huy 12h.
2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest | 2.15 Validated base/target materialization and identity manifest
Dependencies | Dependencies | 2.14 identity contract; accepted revision decisions | 2.14 identity contract; accepted revision decisions | 2.14 identity contract; accepted revision decisions | 2.14 identity contract; accepted revision decisions | 2.14 identity contract; accepted revision decisions | 2.14 identity contract; accepted revision decisions | 2.14 identity contract; accepted revision decisions | 2.14 identity contract; accepted revision decisions
Acceptance criteria | Acceptance criteria | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice. | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice. | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice. | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice. | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice. | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice. | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice. | Validate authorized repository, full SHA and commit object; materialize immutable source without dirty-tree input. Reject invalid identity/SHA, traversal and unsupported entries. Keep arbitrary-repository ingestion outside this slice.
Verification planned | Verification planned | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence. | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence. | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence. | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence. | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence. | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence. | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence. | Immutable Git fixtures, wrong SHA/object/path and unsupported-entry guards; source byte identity evidence.
Traceability / review | Traceability / review | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h. | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h. | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h. | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h. | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h. | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h. | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h. | PB03 prerequisite; PB05/PB19. Reviewer proposed: Tran Hung Khanh. Allocation: Do Ha An 10h.
2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity | 2.16 Component-to-test relationships with provenance and granularity
Dependencies | Dependencies | 2.03/2.04; 2.08/2.09; 2.14 | 2.03/2.04; 2.08/2.09; 2.14 | 2.03/2.04; 2.08/2.09; 2.14 | 2.03/2.04; 2.08/2.09; 2.14 | 2.03/2.04; 2.08/2.09; 2.14 | 2.03/2.04; 2.08/2.09; 2.14 | 2.03/2.04; 2.08/2.09; 2.14 | 2.03/2.04; 2.08/2.09; 2.14
Acceptance criteria | Acceptance criteria | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced. | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced. | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced. | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced. | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced. | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced. | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced. | Map only supported relationships to IDs present in target inventory. Report unresolved mappings explicitly; never infer safe exclusion. Exclude full-suite outcomes/fault labels from mapping inputs. No production selector is introduced.
Verification planned | Verification planned | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings. | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings. | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings. | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings. | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings. | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings. | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings. | Known relationships, unknown test IDs, wrong target and unresolved cases with independently expected mappings.
Traceability / review | Traceability / review | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h. | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h. | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h. | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h. | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h. | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h. | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h. | PB06/PB09; prepares PB22. Reviewer proposed: Pham Phan Hoang Huy. Allocation: Tran Hung Khanh 8h.
2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports | 2.17 Analysis-scope manifest propagated through stage reports
Dependencies | Dependencies | 2.14 manifest design; integrate each stage as produced | 2.14 manifest design; integrate each stage as produced | 2.14 manifest design; integrate each stage as produced | 2.14 manifest design; integrate each stage as produced | 2.14 manifest design; integrate each stage as produced | 2.14 manifest design; integrate each stage as produced | 2.14 manifest design; integrate each stage as produced | 2.14 manifest design; integrate each stage as produced
Acceptance criteria | Acceptance criteria | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage. | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage. | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage. | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage. | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage. | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage. | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage. | Record analyzed files/modules and partial/unsupported/error reasons. Parse/discovery failures differ from no impact. AN owns analysis status; KH owns inventory propagation. Coverage means analysis scope, not runtime test coverage.
Verification planned | Verification planned | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory. | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory. | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory. | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory. | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory. | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory. | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory. | Partial and failure propagation through workflow/report; inspect unsupported inputs and incomplete inventory.
Traceability / review | Traceability / review | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h. | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h. | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h. | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h. | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h. | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h. | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h. | PB06/PB07/PB09/PB20. Reviewer proposed: Nguyen Tan Huy. Allocation: Do Ha An 6h; Tran Hung Khanh 4h.
2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views | 2.18 Validated report loading, navigation and stage-state views
Dependencies | Dependencies | 2.14 contract; 2.06 component; real stage outputs | 2.14 contract; 2.06 component; real stage outputs | 2.14 contract; 2.06 component; real stage outputs | 2.14 contract; 2.06 component; real stage outputs | 2.14 contract; 2.06 component; real stage outputs | 2.14 contract; 2.06 component; real stage outputs | 2.14 contract; 2.06 component; real stage outputs | 2.14 contract; 2.06 component; real stage outputs
Acceptance criteria | Acceptance criteria | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint. | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint. | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint. | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint. | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint. | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint. | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint. | Open real stage output and validate its contract. Distinguish DEMO/real/loading/empty/partial/error. Display revision/path/span and reuse 2.06 evidence items. UI slice is proposed earlier; PB16 history/evaluation dashboard stays in its sprint.
Verification planned | Verification planned | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity. | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity. | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity. | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity. | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity. | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity. | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity. | Real report loading plus invalid/partial/error states; accessible navigation and visible evidence identity.
Traceability / review | Traceability / review | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h. | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h. | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h. | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h. | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h. | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h. | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h. | PB05/PB07 display; supports 2.13. Reviewer proposed: Nguyen Tan Huy. Allocation: Dang Dai Viet 10h.
2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence | 2.19 Cross-module regression cases and reproduction evidence
Dependencies | Dependencies | 2.14 expectations; integrated stage boundaries from 2.13 | 2.14 expectations; integrated stage boundaries from 2.13 | 2.14 expectations; integrated stage boundaries from 2.13 | 2.14 expectations; integrated stage boundaries from 2.13 | 2.14 expectations; integrated stage boundaries from 2.13 | 2.14 expectations; integrated stage boundaries from 2.13 | 2.14 expectations; integrated stage boundaries from 2.13 | 2.14 expectations; integrated stage boundaries from 2.13
Acceptance criteria | Acceptance criteria | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases. | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases. | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases. | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases. | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases. | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases. | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases. | Cover wrong repo/SHA, invalid evidence, stale index, unknown test ID, failed discovery and partial analysis. Expected outcomes are independent of observed output. AN owns identity/evidence cases; KH owns inventory/runner integration cases.
Verification planned | Verification planned | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests. | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests. | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests. | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests. | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests. | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests. | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests. | SmartRegression tests on authorized fixtures/candidates; do not generate tests for input repos or recount task unit tests.
Traceability / review | Traceability / review | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h. | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h. | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h. | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h. | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h. | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h. | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h. | Sprint 2 integration quality. Reviewer proposed: Dang Dai Viet. Allocation: Do Ha An 4h; Tran Hung Khanh 4h.
2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate | 2.20 Bounded PostgreSQL foundation; 24h preliminary estimate
Dependencies | Dependencies | 2.14 contract; minimum-schema/tooling decision checkpoint | 2.14 contract; minimum-schema/tooling decision checkpoint | 2.14 contract; minimum-schema/tooling decision checkpoint | 2.14 contract; minimum-schema/tooling decision checkpoint | 2.14 contract; minimum-schema/tooling decision checkpoint | 2.14 contract; minimum-schema/tooling decision checkpoint | 2.14 contract; minimum-schema/tooling decision checkpoint | 2.14 contract; minimum-schema/tooling decision checkpoint
Acceptance criteria | Acceptance criteria | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate. | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate. | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate. | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate. | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate. | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate. | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate. | Map minimum schema and FK prerequisites to DB Design v1.5. Backend-only config without secrets, versioned migrations, real PostgreSQL integration checks and cross-repo/run/snapshot constraints. Verify transactions/failure/rollback and setup/recovery; artifacts remain separate.
Verification planned | Verification planned | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h. | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h. | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h. | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h. | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h. | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h. | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h. | PostgreSQL migration/round-trip/failure evidence. H1 owns contracts/connection; KH owns migration mechanism/integration checks. Consumers own domain persistence; one migration writer. Re-estimate proposal if slice exceeds 24h.
Traceability / review | Traceability / review | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h. | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h. | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h. | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h. | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h. | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h. | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h. | Supports PB04/PB06/PB09/PB19/PB20. Reviewer proposed: Do Ha An. Allocation: Nguyen Tan Huy 12h; Tran Hung Khanh 12h.
Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours) | Planned allocation and resource needs (hours)
Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort. | Accountable owner is not the full effort allocation. This table is proposed planning only; daily worked-hour logs at rows 44–51 remain actual effort.
Task ID | Member | Member | Member | Planned hours |  | Member allocation | Member allocation | Member allocation | Hours
2.01 | Do Ha An | Do Ha An | Do Ha An | 20 |  | Nguyen Tan Huy | Nguyen Tan Huy | Nguyen Tan Huy | 50
2.02 | Dang Dai Viet | Dang Dai Viet | Dang Dai Viet | 8 |  | Do Ha An | Do Ha An | Do Ha An | 40
2.03 | Pham Phan Hoang Huy | Pham Phan Hoang Huy | Pham Phan Hoang Huy | 16 |  | Pham Phan Hoang Huy | Pham Phan Hoang Huy | Pham Phan Hoang Huy | 52
2.04 | Pham Phan Hoang Huy | Pham Phan Hoang Huy | Pham Phan Hoang Huy | 12 |  | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 50
2.05 | Nguyen Tan Huy | Nguyen Tan Huy | Nguyen Tan Huy | 8 |  | Dang Dai Viet | Dang Dai Viet | Dang Dai Viet | 40
2.06 | Nguyen Tan Huy | Nguyen Tan Huy | Nguyen Tan Huy | 6 |  | Task hours | Task hours | Task hours | 232
2.06 | Dang Dai Viet | Dang Dai Viet | Dang Dai Viet | 6
2.07 | Dang Dai Viet | Dang Dai Viet | Dang Dai Viet | 8 |  | Proposed reserve | Proposed reserve | Proposed reserve | 32
2.08 | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 12 |  | Resource need | Resource need | Resource need | 264
2.09 | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 6 |  | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks. | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks. | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks. | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks.
2.10 | Pham Phan Hoang Huy | Pham Phan Hoang Huy | Pham Phan Hoang Huy | 12 |  | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks. | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks. | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks. | Actual team capacity: pending confirmation. Reserve excludes work already estimated in tasks.
2.10 | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 4
2.11 | Pham Phan Hoang Huy | Pham Phan Hoang Huy | Pham Phan Hoang Huy | 12
2.12 | Dang Dai Viet | Dang Dai Viet | Dang Dai Viet | 8
2.13 | Nguyen Tan Huy | Nguyen Tan Huy | Nguyen Tan Huy | 12
2.14 | Nguyen Tan Huy | Nguyen Tan Huy | Nguyen Tan Huy | 12
2.15 | Do Ha An | Do Ha An | Do Ha An | 10
2.16 | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 8
2.17 | Do Ha An | Do Ha An | Do Ha An | 6
2.17 | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 4
2.18 | Dang Dai Viet | Dang Dai Viet | Dang Dai Viet | 10
2.19 | Do Ha An | Do Ha An | Do Ha An | 4
2.19 | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 4
2.20 | Nguyen Tan Huy | Nguyen Tan Huy | Nguyen Tan Huy | 12
2.20 | Tran Hung Khanh | Tran Hung Khanh | Tran Hung Khanh | 12
Total |  |  |  | 232
Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints | Estimate basis and checkpoints
Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity. | Task hours: original 150h + additions 58h + PostgreSQL 24h preliminary. Reserve 32h is separate; resource need is 264h, not committed team capacity.
No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h. | No baseline re-estimate is approved here. Record proposed additional hours/scope and rationale for team decision if the minimum DB slice exceeds 24h.
Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied. | Do not infer completion from zero tracking values: these are the original workbook values. No new daily progress, actual effort or human approval is supplied.
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Sprint 2 Reports & Dashboards
Sprint goal: Change impact + dependency analysis + RAG retrieval core
Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. |  | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending. | Planning revision: proposed task scope; results and review acceptance remain pending.
Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions | Sprint 2 plan and decisions
Database decision | Database decision | Database decision | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending. | PostgreSQL accepted by user on 2026-10-31. Python/FastAPI remains. ORM/driver, migration tool and minimum schema slice: pending.
Goal | Goal | Goal | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context. | Authorized Python/pytest repo with frozen base/target SHAs: changed components, potential impact paths, evidence, target inventory, test mapping and retrieved context.
Planned task hours | Planned task hours | Planned task hours | 232
Proposed reserve | Proposed reserve | Proposed reserve | 32
Resource need | Resource need | Resource need | 264
Actual capacity | Actual capacity | Actual capacity | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan. | Pending current member availability/commitment. Historical Project Plan assumes 300h per sprint; it does not confirm availability for this revised plan.
Results / acceptance | Results / acceptance | Results / acceptance | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision. | Not measured / pending. No implementation, benchmark accuracy, human approval or actual effort is asserted by this planning revision.
Baseline reconciliation | Baseline reconciliation | Baseline reconciliation | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together. | Backlog original 13 tasks = 150h; Main previously 184h. Revised task plan = 232h. Project Plan 250h = PB-level 195h + 55h overhead; do not add these estimates together.
Dates | Dates | Dates | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied. | Existing workbook dates/statuses retained. Use relative three-week sequencing; no new calendar start/end dates supplied.
Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance | Dependencies and planned acceptance
Week 1 | Week 1 | Week 1 | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop. | 2.14 contracts; 2.15 snapshots; 2.20 minimum-schema checkpoint; retrieval decision. Start 2.13 thin workflow while graph/discovery/index interfaces develop.
Week 2 | Week 2 | Week 2 | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready. | 2.01 → 2.03 → 2.04 → 2.05/2.06; 2.08/2.09 + graph → 2.16; 2.10 → 2.11 → 2.12. Connect domain persistence to 2.20 foundation as ready.
Week 3 | Week 3 | Week 3 | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously. | 2.18 real report inspection; 2.19 cross-module failures; candidate reproduction, demo and human review. 2.17 limitations are designed early and propagated continuously.
Dependency boundary | Dependency boundary | Dependency boundary | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies. | Design/interface readiness may unblock work before implementation is complete. 2.13 integrates incrementally; 2.19 tests integrated boundaries. Avoid circular all-stage dependencies.
Planned DoD | Planned DoD | Planned DoD | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved. | Task AC met, relevant checks with recorded commands/results, correct revision evidence, actual human review and updated docs. Errors/partial states stay visible. These conditions are not marked achieved.
Integrity | Integrity | Integrity | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields. | Potential dependency reachability is not verified behavioral impact. Schema-valid JSON or exit 0 is insufficient business evidence. No fabricated selection/execution fields.
Runner and leakage | Runner and leakage | Runner and leakage | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection. | Input code/conftest/build hooks execute only in isolated runner. No secrets, fault labels or full-suite reference outcomes enter indexing/mapping/retrieval/selection.
UI scope | UI scope | UI scope | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint. | 2.06 owns individual evidence item/payload; 2.18 owns real-report loading/navigation/state handling. Proposed earlier display slice supports PB05/PB07; PB16 history/evaluation stays in its sprint.
Integration scope | Integration scope | Integration scope | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice. | 2.13 owns workflow wiring/smoke/demo. 2.19 owns cross-module regressions. Per-task unit tests stay in their estimates. No work is counted twice.
Later sprints | Later sprints | Later sprints | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice. | Full LLM selection, production execution, benchmark/history dashboard, full dataset and input-repo CI integration remain outside this Sprint 2 slice.
PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required) | PostgreSQL schema mapping (proposed; decision required)
Minimum-slice gate | Minimum-slice gate | Minimum-slice gate | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design. | 2.20 owner H1 with KH; reviewer proposed AN. Confirm exact tables/columns/FK prerequisites before migrations. 24h covers bounded foundation, not the whole cumulative DB design.
Paths / evidence | Paths / evidence | Paths / evidence | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence. | changed_files, code_components, dependency_edges, impact_candidates, evidence_references: proposed needed for the persisted impact slice; exact minimum pending. 2.05 owns domain persistence.
Inventory | Inventory | Inventory | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence. | test_inventories, test_cases: proposed needed for durable target inventory/mapping; minimal fields and constraints pending. 2.08 owns inventory persistence.
Retrieval metadata | Retrieval metadata | Retrieval metadata | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice. | knowledge_indexes, knowledge_chunks: pending retrieval design/minimum-slice decision; metadata needed for 2.10. Keep vector/index implementation a separate explicit choice.
FK prerequisites | FK prerequisites | FK prerequisites | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services. | repositories, analysis_runs, artifacts and referenced user/configuration keys require reconciliation with Sprint 1 design. Exact prerequisite slice pending; do not silently create full auth/configuration services.
Deferred | Deferred | Deferred | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately. | Full authentication/authorization service, history dashboard, Sprint 3 selection/execution tables and Sprint 4 evaluation/CI tables are deferred. Required referential keys are decided separately.
Retrieval checkpoint | Retrieval checkpoint | Retrieval checkpoint | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name. | Select permitted retrieval/embedding approach before 2.10–2.12. DB Design §3.4.8 makes embedding_model non-null; lexical-only requires explicit design reconciliation, never a fake model name.
Persistence boundary | Persistence boundary | Persistence boundary | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time. | 2.20: connection/config, versioned migration mechanism and transaction foundation. 2.05: paths/evidence; 2.08: inventory; 2.10: retrieval metadata. One designated writer per shared migration at a time.
Database acceptance | Database acceptance | Database acceptance | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files. | Real PostgreSQL migration/round-trip checks; reject cross-repo/run/snapshot links; verify failure/transaction rollback and setup/recovery. No actual DSN/secrets in workbook. Large artifacts remain protected files.
Re-estimate handling | Re-estimate handling | Re-estimate handling | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates. | If tables/prerequisites exceed 24h, record proposed additional hours, scope and reason without changing the 232h baseline. Review/debug reserve excludes work already included in task estimates.
Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation | Pending decisions and source reconciliation
Capacity | Capacity | Capacity | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint. | Confirm each member availability against planned allocation. If insufficient, propose scope/resource options; do not silently drop tasks, reassign members or extend sprint.
Revision policy | Revision policy | Revision policy | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user. | Review Sprint 1 revision semantics/Q01–Q10 and candidate authorization before dependent behavior. PR merge is not blanket policy/mentor approval. PostgreSQL engine alone is accepted by the current user.
Outside-scope follow-up | Outside-scope follow-up | Outside-scope follow-up | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here. | Synchronize PostgreSQL and revised Sprint 2 scope in decision register, team-guide and relevant DOCX documents in a separate authorized task. These files are unchanged here.
Sources | Sources | Sources | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3. | User Sprint 2 instructions (2026-10-31); Proposal v1.4 §11.2–11.3 and Appendices C/D; Project Plan v1.1 Sprint 2; Architecture v1.3 impact/retrieval tables; Database Design v1.5 §3.
Repository evidence | Repository evidence | Repository evidence | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed. | Sprint 1 review/closeout handoff and decision register; bootstrap application/adapters and contracts. Current AnalysisReport requires selection; stage contracts are planned under 2.14. No DB integration is claimed.
AI disclosure | AI disclosure | AI disclosure | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied. | OpenAI Codex assisted Sprint 2 planning text, workbook editing and consistency checks in this session. Team review/understanding is pending; no assistance percentage, new signature or mentor approval is supplied.
Task details | Task details | Task details | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate. | See Sprint 2 Backlog rows 55–174 for 20 task briefs/AC/dependencies/reviewers; rows 184–210 for numeric planned allocations. Daily actual-effort tracking remains separate.
Tracking interpretation | Tracking interpretation | Tracking interpretation | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here. | Backlog burn-down/up formulas aggregate existing daily completed-estimate entries. All existing daily entries are blank/zero. No measured progress curve or new actual outcomes are created here.
Member key |  |  | H1 = Nguyen Tan Huy; AN = Do Ha An; H2 = Pham Phan Hoang Huy; KH = Tran Hung Khanh; VI = Dang Dai Viet.

## Sprint 3 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
3.01 | PB10 | Generate validated selection manifest | Tran Hung Khanh | Not started | 14 | 0 | 14 | 0
3.02 | PB10 | Validate inventory membership, partition and target SHA | Tran Hung Khanh | Not started | 10 | 0 | 10 | 0
3.03 | PB11 | Implement evidence/reason inspection for selection decisions | Pham Phan Hoang Huy | Not started | 12 | 0 | 12 | 0
3.04 | PB21 | Integrate LLM proposal generation with structured schema | Pham Phan Hoang Huy | Not started | 16 | 0 | 16 | 0
3.05 | PB21 | Validate LLM outputs against inventory and commit-linked evidence | Pham Phan Hoang Huy | Not started | 12 | 0 | 12 | 0
3.06 | PB22 | Implement conservative dependency + modified + LLM selection policy | Tran Hung Khanh | Not started | 14 | 0 | 14 | 0
3.07 | PB12 | Implement LLM timeout/malformed-output fallback | Tran Hung Khanh | Not started | 10 | 0 | 10 | 0
3.08 | PB12 | Implement unsupported-code/configuration/full-suite fallback rules | Tran Hung Khanh | Not started | 10 | 0 | 10 | 0
3.09 | PB13 | Execute selected tests at frozen target SHA | Tran Hung Khanh | Not started | 14 | 0 | 14 | 0
3.10 | PB14 | Capture per-test outcomes and failure categories | Tran Hung Khanh | Not started | 12 | 0 | 12 | 0
3.11 | PB16 | Build initial impact/selection/execution dashboard | Dang Dai Viet | Not started | 14 | 0 | 14 | 0
3.12 | PB23 | Prepare pilot dataset and fault-bearing cases | Dang Dai Viet | Not started | 12 | 0 | 12 | 0
3.13 | PB04 | Run integrated pilot and record Sprint 3 findings | Nguyen Tan Huy | Not started | 8 | 0 | 8 | 0
|  |  |  | Total | 158 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Tan Huy | [16 empty] | 0
[8 empty] | Do Ha An | [16 empty] | 0
[8 empty] | Pham Phan Hoang Huy | [16 empty] | 0
[8 empty] | Tran Hung Khanh | [16 empty] | 0
[8 empty] | Dang Dai Viet | [16 empty] | 0
0
Update actual worked hours per team member each day. Keep effort logs separate from planned task estimates.
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Sprint 3 Reports & Dashboards
Sprint goal: LLM-assisted test selection + fallback + pilot execution
Record burn-down/burn-up, sprint review evidence, achieved acceptance checks and key decisions. | Burn up Chart

## Sprint 4 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
4.01 | PB15 | Implement analysis history search and run reopening | Dang Dai Viet | Not started | 12 | 0 | 12 | 0
4.02 | PB16 | Implement HTML and JSON report export | Dang Dai Viet | Not started | 16 | 0 | 16 | 0
4.03 | PB17 | Integrate one selected CI/CD platform | Tran Hung Khanh | Not started | 18 | 0 | 18 | 0
4.04 | PB17 | Verify idempotent duplicate-event handling and failure statuses | Tran Hung Khanh | Not started | 10 | 0 | 10 | 0
4.05 | PB18 | Implement predefined evaluation method runner | Dang Dai Viet | Not started | 14 | 0 | 14 | 0
4.06 | PB24 | Run full-suite baseline | Nguyen Tan Huy | Not started | 10 | 0 | 10 | 0
4.07 | PB24 | Run dependency-based baseline | Nguyen Tan Huy | Not started | 10 | 0 | 10 | 0
4.08 | PB24 | Run LLM-based baseline | Pham Phan Hoang Huy | Not started | 10 | 0 | 10 | 0
4.09 | PB24 | Run SmartRegression AI comparison | Nguyen Tan Huy | Not started | 12 | 0 | 12 | 0
4.10 | PB24 | Calculate impact, evidence, reduction, fault-retention, time, cost and fallback metrics | Dang Dai Viet | Not started | 18 | 0 | 18 | 0
4.11 | PB23 | Validate held-out evaluation conditions and document threats to validity | Dang Dai Viet | Not started | 10 | 0 | 10 | 0
4.12 | PB16 | Finalize dashboard, reports and reproducibility evidence | Dang Dai Viet | Not started | 10 | 0 | 10 | 0
4.13 | PB18 | Prepare final evaluation/demo package | Nguyen Tan Huy | Not started | 10 | 0 | 10 | 0
4.14 | PB18 | Final documentation and project retrospective | Nguyen Tan Huy | Not started | 12 | 0 | 12 | 0
|  |  |  | Total | 172 | 0 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Tan Huy | [16 empty] | 0
[8 empty] | Do Ha An | [16 empty] | 0
[8 empty] | Pham Phan Hoang Huy | [16 empty] | 0
[8 empty] | Tran Hung Khanh | [16 empty] | 0
[8 empty] | Dang Dai Viet | [16 empty] | 0
0
Update actual worked hours per team member each day. Keep effort logs separate from planned task estimates.
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 4 Reports
Sprint 4 Reports & Dashboards
Sprint goal: CI/CD + baselines + evaluation + finalization
Record burn-down/burn-up, sprint review evidence, achieved acceptance checks and key decisions. | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Proposal requirements basis | C1SE26 SmartRegression AI Proposal Merged v1.4 | Functional requirements | FR-01–FR-18; NFR-01–NFR-12; BR-01–BR-10
Research references | Rothermel & Harrold (1997); Lewis et al. (2020) | Methodology | Design Science Research + Scrum; 4 sprints / 12 implementation weeks
Scope note | One programming language, one testing framework, GitHub, one CI/CD platform; no test generation or automatic code repair. | Evaluation targets | ≥2 repositories; ≥30 commit pairs; ≥15 verified fault-bearing cases