International School

Capstone Project 1

CMUSE-450

Project Plan

Version 1.1

SmartRegression AI: LLM/RAG-based Change Impact Analysis and Test Selection

Created by C1SE.26

Huy, Nguyen Tan - 29211154944

An, Do Ha - 29211258599

Huy, Pham Phan Hoang - 29311156999

Khanh, Tran Hung - 29219065410

Viet, Dang Dai - 29211155820

Capstone Project 1 - Mentor:

JAN SAMUELSSON                         Signature                         Date

PROJECT INFORMATION

| Project acronym | SmartRegression AI |  |  |  |
| --- | --- | --- | --- | --- |
| Project Title | SmartRegression AI: An LLM- and RAG-Based Change Impact Analysis and Regression Test Selection System |  |  |  |
| Start Date | 23 Aug. 2026 | End Date | 13 Dec. 2026 |  |
| Lead Institution | International School, Duy Tan University |  |  |  |
| Project Mentor | JAN SAMUELSSON |  |  |  |
| Scrum master / Project Leader & contact details | Huy, Nguyen Tan Email: nguyentanhuy46205@gmail.com Tel: 0932401249 ID: 29211154944 |  |  |  |
| Partner Organization | Duy Tan University |  |  |  |
| Project Web URL |  |  |  |  |
| Student ID | Name | Email |  | Tel |
| 29211154944 | Huy, Nguyen Tan | nguyentanhuy46205@gmail.com |  | 0932401249 |
| 29211258599 | An, Do Ha | Anha0664@gmail.com |  | 0815737920 |
| 29211156999 | Huy, Pham Phan Hoang | phamphanhoanghuy2005@gmail.com |  | 0932509973 |
| 29219065410 | Khanh, Tran Hung | Thungkhanh19@gmail.com |  | 0783494325 |
| 29211155820 | Viet, Dang Dai | vdang9721@gmail.com |  | 0384165721 |

# DOCUMENT INFORMATION

| Document title | Project Plan |  |  |
| --- | --- | --- | --- |
| Author(s) | Team C1SE.26 - all members |  |  |
| Role | Project team authors and workstream owners |  |  |
| Date | 08 Oct. 2026 | File Name | C1SE.26_ProjectPlan_v1.1.docx |
| URL |  |  |  |
| Access | Project Team, Mentor, and CMU Program |  |  |

# REVISION HISTORY

| Version | Date | Comments | Author | Approval |
| --- | --- | --- | --- | --- |
| 1.0 | 11 Sep. 2026 | Initial Project Plan for mentor review | All members | Pending mentor review |
| 1.1 | 08 Oct. 2026 | Aligned WBS, detailed schedule, and milestones with new Product Backlog and Proposal v1.4. | Viet, Dang Dai | Pending mentor review |

Table of Contents

1.	PROJECT OVERVIEW	1

1.1.	Project Description	1

1.2.	Scope and Purpose	1

1.3.	Assumptions and Constraints	2

1.4.	Project Objectives	3

1.5.	Critical Dependencies	4

1.6.	Project Risk	5

2.	PROJECT DEVELOPMENT APPROACH	6

2.1.	Technical Process	6

2.2.	Quality Management	8

2.3.	Test Strategy	9

2.4.	Integration Testing Strategy	10

2.5.	System Testing Strategy	10

3.	ESTIMATION	11

3.1 Effort	11

3.2 Schedule	11

3.3 Resource	17

3.4 Infrastructure	17

3.5 Training Plan	19

3.6 Cost	20

4.	PROJECT ORGANIZATION	22

4.1.	Organization Structure	22

4.2.	Project Team	22

5.	COMMUNICATION & REPORTING	24

5.1.	Communication methodology	24

5.2.	Communication and report	25

6.	CONFIGURATION MANAGEMENT	27

Table of Tables

Table 1. Project Description	1

Table 2. Assumptions and Constraints	2

Table 3. Standard Objectives	3

Table 4. Project risk	5

Table 5. Strategy for Meeting Quality Objectives	8

Table 6. Project Milestone & Deliverables	11

Table 7. Detailed schedule	13

Table 8. Resource	17

Table 9. Infrastructure	17

Table 10. Training plan	19

Table 11. Cost person/hours	20

Table 12. Total cost estimate	21

Table 13. Detailed cost description	21

Table 14. Scrum Team	23

Table 15.  Responsibilities	24

Table 16. Communication methodology	25

Table 17. Communication and report	25

Table of Figures

Figure 1. Work breakdown structure	13

# PROJECT OVERVIEW

## Project Description

Table 1. Project Description

| Project code | C1SE.26 |  |  |
| --- | --- | --- | --- |
| Customer | QA teams, DevOps Engineers, and Software Developers |  |  |
| Project Type | Academic research and development |  |  |
| Project Category | Empirical software engineering / AI Integration | Scrum master | Huy, Nguyen Tan |
| Application type | AI-driven Developer Testing Tool |  |  |

## Scope and Purpose

1.2.1 Purpose

SmartRegression AI provides an intelligent, automated test selection mechanism for software development teams by utilizing Large Language Models (LLMs) and Retrieval-Augmented Generation (RAG). It aims to analyze Git commit diffs, accurately identify impacted code components, and select only the most relevant regression tests. This approach prevents the unnecessary execution of the entire test suite, thereby significantly reducing CI/CD execution time and computing costs without sacrificing quality.

1.2.2 Scope

- Git Repository Integration: Connect to a supported Git repository to obtain changes between two commits or an updated pull request.

- Change Impact Analysis: Analyze the Git Diff to explicitly identify changed functions, classes, modules, and their related dependency relationships.

- Test Collection & RAG Indexing: Collect all existing automated tests within the supported project. Build a retrieval index encompassing the source code, test code, and project documentation.

- LLM-Assisted Regression-Test Selection: Retrieve relevant project context (via RAG) and provide it to the LLM to recommend existing tests. The system must explain selected/skipped decisions based on source location, dependencies, and commit evidence.

- Execution & Validation: Validate the returned test identifiers and evidence. Expand the selection or execute the full test suite (fallback) when the analysis is incomplete, LLM output is invalid, or evidence cannot be verified. Execute the selected tests and record results and execution time.

- Reporting & Delivery Boundary: Provide a dashboard/report comparing selected-test versus full-suite execution. Experimentally integrate the workflow with one CI/CD platform. Deliver a reproducible research benchmark including repository versions, baselines, evaluation data, and metric results.

- Excluded Scope: The MVP supports only one programming language and one testing framework. It focuses solely on selecting existing tests, excluding automatic test generation and automatic code repair.

## Assumptions and Constraints

Table 2. Assumptions and Constraints

| # | Description | Note |
| --- | --- | --- |
| Assumptions |  |  |
| 1 | Selected repositories expose repeatable tests that exercise the changed components and can be built or tested in a controlled environment. | Testability |
| 2 | Git history and source/test artifacts can be accessed for the selected repositories. | Access / Technical |
| 3 | Relevant source code, tests, and documentation can be indexed and retrieved for analysis. | Retrieval Capability |
| 4 | The full test suite can be executed to provide an independent comparison baseline. | Evaluation Baseline |
| 5 | Each member can contribute an average of 20 project hours per week during the 12-week active development phase, generating a total development capacity of 1,200 person-hours across four 3-week sprints. | Capacity assumption |
| Constraints |  |  |
| 1 | The MVP, dataset, experiments, evaluation, and final report must be completed within the project schedule. | Schedule |
| 2 | The MVP is limited to one programming language and one testing framework. | Scope |
| 3 | Suitable repositories must provide Git history, automated tests, and a reproducible build/test environment. | Data limitation |
| 4 | Experiments should use reproducible repository versions and controlled test environments; production systems are not required for the MVP. | Safety / Environment |
| 5 | LLM calls, retrieval, dependency analysis, and test execution consume computational resources, so analysis cost and execution time must be measured. | Resources / Cost |
| 6 | Labeled impact data and known defects may not cover every real-world dependency or regression pattern, so limitations and threats to validity must be reported. | Research validity |

## Project Objectives

1.4.1 Standard Objectives

Table 3. Standard Objectives

| Metrics | Unit | Committed | Note |
| --- | --- | --- | --- |
| Development Phase Start | dd-mm-yyyy | 07-09-2026 | Start of Sprint 1 (Development phase) |
| Development Phase End | dd-mm-yyyy | 29-11-2026 | End of Sprint 4 (Evaluation & Feature freeze) |
| Team Size | Person | 5 | Student team |
| Official duration | Workdays | 80 | Sixteen calendar weeks |
| Active sprint duration | Workdays | 60 | Four three-week sprints |
| Work hours per day per member | Person-hour | 4 | Agreed capacity |
| Total team capacity | Person-hour | 1,200 | Includes 200-hour reserve |

1.4.2 Specific Objectives

Functional and Research Objectives

- Objective 1 - Change Impact Analysis and Dependency Mapping: Analyze the changes between two Git commits or an updated pull request and identify changed functions, classes, modules, and related dependency relationships. This will be evaluated using Change Impact Precision and Recall on labeled evaluation data by the end of Week 6.

- Objective 2 - RAG-Assisted Evidence and Regression-Test Selection: Retrieve relevant source code, test code, and documentation to provide context to the LLM, and recommend existing regression tests with explanations. This will be evaluated via Evidence Accuracy, Test Reduction Rate, Fault Detection Retention, and Missed Fault Rate by the end of Week 9.

- Objective 3 - Experimental Comparison and Evaluation: Compare SmartRegression AI with full-suite execution, dependency-based selection, and LLM-based selection baselines. The evaluation will report Change Impact Precision/Recall, Evidence Accuracy, Test Reduction Rate, Fault Detection Retention, Missed Fault Rate, End-to-End Time Reduction, and LLM Cost/Token Usage by the end of Week 12.

Quality Goals

- Traceability and Evidence: Ensure that analysis results are traceable to source locations, dependency relationships, and commit versions where applicable.

- Fallback Reliability: The selection mechanism must fall back to a larger or full test set when parsing/dependency analysis is incomplete, LLM output is invalid, test identifiers are unknown, or evidence cannot be verified.

- Reproducibility: Evaluation must use fixed repository commits, recorded model/configuration versions, and repeatable execution conditions to explicitly separate flaky tests and infrastructure failures from actual regression faults.

- Cost Measurement: The system must record analysis, indexing/retrieval, LLM processing, test-execution time, and token usage to accurately assess the cost data of the solution.

## Critical Dependencies

Critical dependencies include: (1) repeatable tests that exercise the changed components and can be built or tested in a controlled environment; (2) accessible Git history, source code, test code, and documentation for the selected repositories; (3) stable availability and responsiveness of the selected LLM service and retrieval/indexing technologies; (4) the ability to execute the full test suite to provide an independent comparison baseline; and (5) obtaining a reliable set of labeled impact data and known defects to validate the system's accuracy.

## Project Risk

Table 4. Project risk

| Risk | Description | P | I | E (P x I) | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| Incomplete Impact Ground Truth | It may be difficult to obtain a complete labeled set of truly affected components. | 4 | 5 | 20 | Use multiple repositories, versioned changes, dependency evidence and known defects; document labeling limitations. |
| RAG Context Quality | Retrieved context may be incomplete or irrelevant and can affect LLM analysis. | 4 | 4 | 16 | Evaluate retrieval quality, preserve evidence, tune retrieval scope and use fallback behavior when context is insufficient. |
| LLM Incorrect Reasoning | The LLM may produce incorrect impact or test-selection explanations. | 4 | 5 | 20 | Require evidence tracing, compare against labeled data and baselines, and do not rely on unsupported LLM claims. |
| Test Selection Misses Faults | Reducing the test set may omit a test that detects a regression fault. | 4 | 5 | 20 | Compare against full-suite execution, measure Fault Detection Retention and Missed Fault Rate, and expand to a larger/full set when analysis is insufficient. |
| Repository / Build Limitations | Open-source repositories may not build reproducibly or may lack sufficient tests. | 4 | 4 | 16 | Screen candidate repositories early and keep a reproducible benchmark environment. |
| LLM Cost / Latency | Repeated retrieval and LLM calls may offset the time saved by running fewer tests. | 3 | 4 | 12 | Measure End-to-End Time Reduction and LLM Cost/Token Usage; cache reusable context where appropriate. |
| Schedule Delay | Integration of dependency analysis, RAG, LLM, test execution and evaluation may exceed the project schedule. | 3 | 5 | 15 | Freeze the MVP scope early, prioritize the two core functions, and defer optional extensions. |
| Team Technical Competency Gap | The team has limited experience in AST parsing, RAG integration, and empirical evaluation. | 4 | 4 | 16 | Run focused training and an end-to-end spike; use pair programming, code reviews, and mentor checkpoints. |
| Reduced Team Availability | Academic workload, examinations, or personal commitments may reduce planned contributions from team members. | 4 | 5 | 20 | Maintain a capacity calendar, review workload weekly, assign backup owners, and reallocate work immediately. |
| Key-Person Dependency | Core knowledge of AI/LLM integration or CI/CD pipelines is concentrated in specific members. | 3 | 5 | 15 | Pair a backup owner with the lead developers, automate setup processes, and maintain shared documentation. |

# PROJECT DEVELOPMENT APPROACH

## Technical Process

SmartRegression AI uses Design Science Research (DSR) to build and empirically evaluate the proposed change-impact and test-selection artifact, while Scrum controls delivery through four three-week sprints. The team manages work in Jira, maintains code and documents in GitHub, runs automated checks in CI/CD platforms, and packages environments for reproducible evaluation.

2.1.1 Reasons for Selecting the Approach

DSR fits the research objective because the team must design an AI-driven artifact, demonstrate it on controlled repositories, and compare its performance with established full-suite and dependency-based baselines. Scrum provides short feedback cycles, visible ownership, and regular opportunities to re-estimate novel AST parsing and RAG integration work. The combination supports both prototype completion and defensible scientific evaluation within the twelve-week active schedule.

2.1.2 Design Science Research and Scrum

Design Science Research Cycle

- Problem identification: Establish the regression-testing costs and change-impact gaps faced by development teams.

- Objective definition: Finalize research questions, evaluation baselines (full-suite, dependency-based, LLM-based), metrics, and validity controls.

- Design and construction: Build AST parsing, dependency mapping, RAG indexing, LLM test-selection logic, evidence reporting, and fallback components.

- Demonstration and evaluation: Execute controlled experiments on the selected repositories using labeled datasets with reproducible repository versions.

- Communication: Report precision, recall, test reduction rates, LLM costs, and reproducibility evidence in the final technical report.

Scrum Delivery Model

- The Product Backlog contains research, engineering, dataset labeling, and project-management work items.

- Four three-week sprints cover research foundation, change impact/retrieval core, LLM-assisted selection, and full evaluation.

- Sprint Planning confirms capacity, dependencies, risk responses, owners, and the evidence required to accept each work item.

- Sprint Review demonstrates the increment and checks progress against the research objectives and Capstone deliverables.

Scrum and Research Roles

- Project Leader and Product Owner: Huy, Nguyen Tan maintains priorities, stakeholder alignment, scope, and experimental governance.

- Scrum Master: Huy, Nguyen Tan facilitates planning, reviews, retrospectives, risk escalation, and removal of delivery blockers.

- Development Team: All five members design, implement, test, label datasets, review, and demonstrate the agreed increment.

- Mentor: Jan Samuelsson reviews project direction, research rigor, progress, and major scope or validity decisions.

Project Controls

- Scope baseline: In-scope and out-of-scope boundaries defined in the approved proposal (e.g., restricted to one programming language and one framework) control backlog admission.

- Traceability: Every committed task links to an objective, requirement, deliverable, owner, test, or research artifact.

- Feature freeze: Major feature development ends on 18 Nov 2026 so evaluation, baseline comparisons, and critical fixes remain protected.

- Change control: Scope changes require an impact assessment covering effort, schedule, risk, evidence, and deferred work.

- Evidence control: Configurations, LLM prompts, Ground Truth datasets, logs, evaluation results, and analysis scripts are versioned with release tags.

- Risk control: Probability, impact, triggers, mitigation actions, and ownership are reviewed at least weekly.

- Documentation control: Document owners update affected specifications and traceability records in the same sprint as the change.

- Definition of Done: Code is peer-reviewed, automated tests pass, fallback logic is verified, acceptance evidence is attached, documentation is updated, and no unresolved critical defect remains.

Core Collaboration and Engineering Tools

- Jira: Manages the product backlog, sprint boards, estimates, acceptance criteria, dependencies, risks, and progress evidence.

- Git and GitHub: Manage branches, pull requests, reviews, tagged releases, documents, datasets, and issue links.

- CI/CD Platforms (e.g., GitHub Actions): Provide repeatable builds, tests, linting, experimental execution, and artifact packaging.

Expected Management Benefits

- Incremental delivery enables early validation of the highest-risk technical assumptions (e.g., AST parsing complexity and RAG integration) and reduces late integration failure.

- Fixed token budgets, frozen configurations, and retained evidence support fair comparison between SmartRegression AI and the established baselines.

## Quality Management

Table 5. Strategy for Meeting Quality Objectives

| Quality Strategy | Expected Result |
| --- | --- |
| Maintain requirement-to-design-to-test-to-evidence traceability for every committed feature and experiment. | Controls scope, supports review, and demonstrates that each accepted result is backed by verifiable evidence. |
| Require issue-linked pull requests, at least one peer review, linting, automated tests, and successful builds before merge. | Detects defects early, spreads technical knowledge, and protects the release branch. |
| Version dependencies, LLM prompts, configurations, datasets, analysis scripts, and report outputs. | Enables repeatable experiments and fair comparison between SmartRegression AI and the baselines. |
| Peer-review the labeled dataset (e.g., 50 labeled commit pairs) and verify fault-detecting tests independently. | Improves ground-truth accuracy and reduces false conclusions caused by incorrect labels or incomplete dependency mapping. |
| Execute tests in isolated non-production environments and redact credentials or sensitive code/data from LLM inputs. | Reduces privacy, operational, and security risks during LLM analysis and test execution. |
| Apply sprint quality gates, weekly risk/capacity reviews, and a Feature freeze on Nov 18. | Protects evaluation time and keeps essential research and Capstone deliverables achievable. |

## Test Strategy

Unit Testing

- Objective: Verify isolated Git diff extraction, AST parsing utilities, vector chunking, prompt generation, and fallback logic.

- Technique: Use Python testing frameworks (e.g., Pytest or Unittest) with deterministic code snippets, mock Git histories, boundary-value cases, and mock LLM API responses.

- Completion criteria: All critical modules pass; changed modules have relevant tests; no open Severity 1 or Severity 2 unit defect remains.

- Special considerations: Test boundary cases for token limits, invalid JSON LLM outputs, and unsupported Python syntax structures.

Integration Testing

- Objective: Verify data flow among Git integration, AST mapping, RAG retrieval, LLM analysis, execution module, and the dashboard.

- Technique: Use local mock repositories, isolated execution environments, and API mockers for LLM endpoints.

- Completion criteria: The workflow reaches the expected selection list or successfully triggers the fallback mechanism without crashing.

- Special considerations: Isolate test data, restore state between experiments, and verify CI/CD exit codes separately.

Algorithm and Fallback Testing

- Objective: Determine whether SmartRegression AI correctly triggers fallback mechanisms when parsing fails, test identifiers are unknown, or LLM hallucinations occur.

- Technique: Inject malformed source code, incomplete dependencies, or configure the mock LLM to return invalid test IDs to force fallback execution.

- Completion criteria: Fallback to the full test suite is successfully triggered, and the specific fallback reason is recorded in the logs.

Research Evaluation and Performance Testing

- Run SmartRegression AI against full-suite execution, dependency-based, and LLM-only baselines.

- Report precision, recall, test reduction rate, fault detection retention, missed faults, end-to-end time, and token cost/usage.

- The evaluation will measure impact-analysis Precision and Recall, test reduction rate, and fault-detection retention using standard empirical software engineering definitions. The 50-commit-pair evaluation dataset will be reviewed independently by two reviewers to verify the ground-truth labels and resolve disagreements before evaluation.

Test Environment and Automation

- Automate linting, unit tests, and smoke experiments in CI/CD (e.g., GitHub Actions). Execute full research experiments in isolated local or CI environments to ensure cost control.

Completion and Evidence

- A test activity is accepted only when its configuration, retrieved context, LLM prompt/response, expected result, actual result, and defect links are recorded.

## Integration Testing Strategy

- Objective: Verify that supported components exchange normalized and complete data throughout an end-to-end change impact analysis.

- Components: Git diff extractor, AST mapper, Vector indexer, LLM service interface, fallback validator, test executor, and HTML dashboard.

- Scenarios: Baseline discovery, full suite fallback trigger, successful subset test selection, and CI/CD report generation.

- Tools: Pytest, local mock repositories, mock CI/CD runners, and GitHub Actions.

- Data and environment: Reset repository fixtures between runs; redact credentials and sensitive code from LLM inputs.

- Completion criteria: All critical interfaces pass, evidence fields are complete, and failures are reproducible from a versioned configuration.

## System Testing Strategy

- Objective: Validate the complete SmartRegression AI prototype, research workflow, and Capstone deliverable package against the approved requirements.

Techniques

- Functional and end-to-end testing of configuration, experimental execution, and dashboard reporting.

- Baseline comparison testing using the Ground Truth dataset (50 labeled commit pairs).

- Safety and privacy testing for environment allowlists, secret redaction, and token budget enforcement.

Completion Criteria

- All committed functional and non-functional requirements are verified with traceable evidence.

- No unresolved Severity 1 or Severity 2 defect remains.

- The benchmark contains 50 reproducible labeled commit pairs, and the system executes baseline comparisons successfully.

Special Considerations

- Experiments must use repeatable repository versions and controlled LLM parameters (e.g., temperature). Repeated trials, equal token budgets, and documented environment versions are required for defensible scientific conclusions.

# ESTIMATION

## 3.1 Effort

Effort is estimated bottom-up from the Work Breakdown Structure. The planning baseline assumes five members working an average of 20 project hours per person per week during the 12-week active development phase (Sprints 1-4). This yields 300 person-hours of capacity per three-week sprint, totaling 1,200 person-hours for development. Planned development work totals 1,000 person-hours, retaining exactly 200 hours as a capacity reserve. Activities in the Initiation and Start-Up phases (160 hours) and the Closure and Final Release phase (180 hours) are executed outside this active 12-week window, bringing the total project effort to 1,340 hours.

## 3.2 Schedule

3.2.1 Project Milestones and Deliverables

Table 6. Project Milestone & Deliverables

| # | Milestone | Start | Finish | Deliverables |
| --- | --- | --- | --- | --- |
| 1 | Initiation | 23 Aug. 2026 | 30 Aug. 2026 | Proposal baseline; research brief; capacity and risk review. |
| 2 | Start-Up | 31 Aug. 2026 | 6 Sep. 2026 | Project Plan; backlog; repository/Jira; standards; CI skeleton. |
| 3 |  |  |  |  |
| 3.1 | Sprint 1 | 7 Sep. 2026 | 27 Sep. 2026 | Git repository connected, testing environment configured, change range selection implemented, and reproducible evaluation dataset prepared. |
| 3.2 | Sprint 2 | 28 Sep. 2026 | 18 Oct. 2026 | Change impact computed, evidence mapped, existing tests discovered, RAG index built, and change-relevant context retrieval implemented. |
| 3.3 | Sprint 3 | 19 Oct. 2026 | 8 Nov. 2026 | LLM output validated, selection manifest generated with reasons, fallback policy applied, and selected tests executed with results inspected. |
| 3.4 | Sprint 4 | 9 Nov. 2026 | 29 Nov. 2026 | CI/CD platform integrated, reports exported, analysis history browsed, and baseline metrics evaluated. Feature freeze on 18 Nov 2026; post-freeze work strictly prioritizes critical bug fixes, evaluation, and documentation. |
| 4 | Closure and Mentor Review | 30 Nov. 2026 | 6 Dec. 2026 | Corrected deliverables; QA; traceability audit; demo rehearsal. |
| 5 | Final Release | 7 Dec. 2026 | 13 Dec. 2026 | Tagged release; reproducibility package; scientific report; slides; poster; video. |

3.2.2 Work Breakdown Structure

Figure 1. Work breakdown structure

Work packages are traced to sprint tasks, owners, acceptance evidence, and Capstone deliverables.

3.2.3 Detailed Schedule

Table 7. Detailed schedule

| No. | Task Name | Effort (person-hours) | Start | Finish | Team Capacity |
| --- | --- | --- | --- | --- | --- |
| 1 | 1. Initiation and Start-Up (Combined Phase) | 160 | 23 Aug 2026 | 06 Sep 2026 | 200 |
| 1.1 | Confirm scope, research problem, and metrics | 40 |  |  |  |
| 1.2 | Complete proposal baseline and literature review | 40 |  |  |  |
| 1.3 | Create Project Plan, WBS, and risk registry | 40 |  |  |  |
| 1.4 | Set up GitHub, Jira, CI skeleton, and local environments | 40 |  |  |  |
| 2 | Development Phase (Sprints 1-4) | 1000 | 07 Sep 2026 | 29 Nov 2026 | 1200 |
| 2.1 | Sprint 1 Goal: Git Integration & Components Mapping | 250 | 07 Sep 2026 | 27 Sep 2026 | 300 |
| 2.1.1 | PB01: Connect authorized GitHub repository | 15 |  |  |  |
| 2.1.2 | PB02: Configure testing environment | 15 |  |  |  |
| 2.1.3 | PB03: Select and freeze change range | 20 |  |  |  |
| 2.1.4 | PB04: Start and monitor analysis | 15 |  |  |  |
| 2.1.5 | PB23: Prepare reproducible evaluation dataset | 30 |  |  |  |
| 2.1.6 | Sprint 1 overhead (code review, ceremonies, labeling) | 155 |  |  |  |
| 2.2 | Sprint 2 Goal: RAG Indexing & Impact Report | 250 | 28 Sep 2026 | 18 Oct 2026 | 300 |
| 2.2.1 | PB05: Review code changes | 25 |  |  |  |
| 2.2.2 | PB06: Compute potential impact | 35 |  |  |  |
| 2.2.3 | PB07: Inspect impact evidence | 25 |  |  |  |
| 2.2.4 | PB08: Find review starting points | 20 |  |  |  |
| 2.2.5 | PB09: Discover existing target tests | 25 |  |  |  |
| 2.2.6 | PB19: Build RAG project index | 35 |  |  |  |
| 2.2.7 | PB20: Retrieve change-relevant context | 30 |  |  |  |
| 2.2.8 | Sprint 2 overhead (integration testing, ceremonies) | 55 |  |  |  |
| 2.3 | Sprint 3 Goal: LLM Selection, Execution & Dashboard | 250 | 19 Oct 2026 | 08 Nov 2026 | 300 |
| 2.3.1 | PB10: Generate and validate selection manifest | 30 |  |  |  |
| 2.3.2 | PB11: Explain test-selection reasons | 30 |  |  |  |
| 2.3.3 | PB12: Apply fallback policy | 30 |  |  |  |
| 2.3.4 | PB13: Execute selected or full tests | 30 |  |  |  |
| 2.3.5 | PB14: Inspect test results | 30 |  |  |  |
| 2.3.6 | PB21: Validate LLM output | 30 |  |  |  |
| 2.3.7 | PB22: Implement selection policy | 25 |  |  |  |
| 2.3.8 | Sprint 3 overhead (pilot testing, ceremonies) | 45 |  |  |  |
| 2.4 | Sprint 4 Goal: CI/CD & Baseline Comparison | 250 | 09 Nov 2026 | 29 Nov 2026 | 300 |
| 2.4.1 | PB15: Browse analysis history | 20 |  |  |  |
| 2.4.2 | PB16: View and export reports | 35 |  |  |  |
| 2.4.3 | PB17: Integrate one CI/CD platform | 30 |  |  |  |
| 2.4.4 | PB18: Run predefined evaluation methods | 35 |  |  |  |
| 2.4.5 | PB24: Evaluate metrics and baselines | 40 |  |  |  |
| 2.4.6 | Sprint 4 Feature freeze (Nov 18), critical bug fixes, and sprint ceremonies | 90 |  |  |  |
| 3 | Closure and Final Release | 180 | 30 Nov 2026 | 13 Dec 2026 | 200 |
| 3.1 | Apply mentor feedback and conduct traceability audit | 50 |  |  |  |
| 3.2 | Draft Scientific Technical Report and documentation | 60 |  |  |  |
| 3.3 | Prepare presentation slides, poster, and demo video | 50 |  |  |  |
| 3.4 | Tag final release and Capstone defense rehearsal | 20 |  |  |  |

3.2.4 Project Schedule

The detailed calendar is maintained in the Jira sprint backlog. Table 7 is the approved planning baseline; task-level changes must preserve milestone dates, declared capacity, and the feature-freeze commitment unless a documented change request is approved.

## 3.3 Resource

Table 8. Resource

| Name | Roles | Responsibilities |
| --- | --- | --- |
| Huy, Nguyen Tan | Project Leader / Research & Integration | Coordinate project scope, risks, research methodology, and system integration. Facilitate sprint ceremonies, manage Jira backlog, and remove team blockers |
| An, Do Ha | Change Impact Analysis / Backend | Implement Git repository integration, Git Diff parsing, Python AST dependency mapping, and core backend services. |
| Huy, Pham Phan Hoang | LLM & RAG / AI Integration | Build RAG indexing and retrieval engine, design LLM prompt engineering, and implement JSON output validation. |
| Khanh, Tran Hung | Regression Test Selection / CI/CD | Implement test selection logic, fallback mechanisms (full suite trigger), and isolated test execution environments. |
| Viet, Dang Dai | Dataset, Dashboard, and Evaluation | Extract and label the 50-commit-pair ground truth dataset, execute baseline experiments, calculate metrics, and build the evaluation dashboard. |

## 3.4 Infrastructure

Table 9. Infrastructure

| Work/Product | Purpose | Expected Availability | Note |
| --- | --- | --- | --- |
| Development Environment |  |  |  |
| Visual Studio Code | Source code, configuration, documentation, and debugging | Initiation through closure | Free |
| Python 3.x | Core implementation language for AST dependency parsing, RAG, and backend integration. | Sprint 1 onward | Version pinned in repository |
| Local Vector Database (e.g., FAISS or ChromaDB) | Indexing and retrieving source code, test code, and project documentation for RAG context. | Sprint 2 onward | Open source |
| External LLM API (e.g., OpenAI or Gemini) | Cloud-based LLM service for impact reasoning and test selection (offloading heavy processing from local machines). | Sprint 3 onward | Token budget monitored |
| Python Testing Framework (e.g., Pytest) | Executing existing automated tests and verifying fallback logic. | Sprint 1 onward | Selected during spike |
| HTML / React / Chart.js | Building the evaluation dashboard and result visualization. | Sprint 3 onward | Open source |
| SQLite or PostgreSQL | Relational database to store the 50-commit-pair evaluation dataset, LLM test-selection responses, token costs, and experiment metadata for the dashboard. | Sprint 1 onward | Local storage |
| Hardware and Execution Environment |  |  |  |
| Team laptops | Development, review, local experiments, and demonstrations | Entire project | Existing equipment |
| Docker Engine/Desktop | Isolated and repeatable application, database, and mock-service environments | Start-Up onward | No production access |
| Collaboration and Delivery Tools |  |  |  |
| Git and GitHub | Source, document, dataset, issue, review, and release version control | Start-Up onward | Protected main branch |
| GitHub Actions | Automated tests, CI/CD integration, and batch execution of experiments. | Start-Up onward | Fixed CI budgets |
| Jira | Backlog, sprint, estimation, risk, dependency, and evidence tracking | Initiation onward | Team board |
| Google Drive, Zalo, and Zoom | Formal document sharing, daily coordination, and remote meetings | Entire project | Repository remains source of truth for versioned artifacts |

## 3.5 Training Plan

Table 10. Training plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Technical |  |  |  |
| Python AST Parsing and Git Diff API Integration | An, Do Ha | Week 1, 8 hours | Waive after successful AST dependency extraction prototype. |
| Vector Database (FAISS/ChromaDB), RAG, and Prompt Engineering | Huy, Pham Phan Hoang; Huy, Nguyen Tan | Weeks 1-2, 10 hours | Waive after RAG retrieval and LLM JSON output validation PoC. |
| Test Isolation, Pytest Integration, and Fallback Logic | Khanh, Tran Hung; An, Do Ha | Week 2, 6 hours | Waive after fallback execution demonstration. |
| Dataset Labeling Protocol and Evaluation Metrics Calculation | Viet, Dang Dai; Huy, Nguyen Tan | Weeks 1-2, 6 hours | Waive after baseline metric script and dataset review. |
| Experimental design and data analysis | Nguyen Tan Huy; Viet | Weeks 1-3, 8 hours | Waive after protocol review |
| React/Chart.js evidence dashboard | Viet; Khanh | Week 2, 4 hours | Waive after dashboard spike |
| Process and Quality |  |  |  |
| Scrum, Jira, estimation, and capacity tracking | All members | Start-Up, 4 hours | Mandatory unless mentor approves |
| GitHub workflow, code review, testing, and secret handling | All members | Start-Up, 4 hours | Mandatory |
| Reproducible experiments and technical documentation | All members | Sprint 1, 4 hours | Mandatory |

## 3.6 Cost

3.6.1 Cost Person-Hours

Table 11. Cost person/hours

| Full Name | Role | Actual Salary Rate (USD/hour) |
| --- | --- | --- |
| Huy, Nguyen Tan | Project Leader / Team Member | $2 |
| An, Do Ha | Team Member | $2 |
| Huy, Pham Phan Hoang | Team Member | $2 |
| Khanh, Tran Hung | Team Member | $2 |
| Viet, Dang Dai | Team Member | $2 |

3.6.2 Total Cost Estimate

Table 12. Total cost estimate

| No. | Cost Item | Basis | Unit Price | Amount | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| 1 | Student engineering labor | Active development capacity (12 weeks, including reserve) | $2 | 1200 | $2,400 |
| 2 | Cloud/CI contingency | Cash reserve | $1 | 50 | $50 |
| 3 | Poster and demo materials | Cash reserve | $1 | 50 | $50 |
| 4 | Project contingency | Cash reserve | $1 | 50 | $50 |
|  |  |  |  | Total cash cost | $2,550 |

Table 13. Detailed cost description

| Description | Amount | Unit |
| --- | --- | --- |
| Number of team members | 5 | Person |
| Planned work hours per day per member | 4 | Hour |
| Working days per week | 5 | Day |
| Active sprint duration | 12 | Week |
| Budgeted development workdays | 60 | Day |
| Active development capacity (Sprints 1-4) | 1,200 | Person-hour |
| Capacity reserve | 200 | Person-hour |
| Expected cash contingency | 150 | USD |

- Note: The student engineering labor budget is based on the allocated capacity of 1,200 person-hours for the 12-week active development phase, including a 200-hour capacity reserve. The 160 hours allocated to Initiation and the 180 hours allocated to Closure are excluded from this labor budget and treated as academic project activities.

# PROJECT ORGANIZATION

SmartRegression AI uses a small cross-functional Scrum team in which ownership follows the technical workstreams defined in the proposal. The structure gives every critical component a primary owner while code review, testing, documentation, and sprint accountability remain shared.

The team depends on timely communication, balanced workload, mentor feedback, reproducible environments, and shared operational knowledge. Backup ownership and written runbooks reduce the risk created by the concentration of experimental knowledge and CI/CD operations.

## Organization Structure

The Project Leader coordinates scope, schedule, risk, stakeholder communication, and research governance. Four engineering and evaluation workstreams execute in parallel where dependencies allow. Pull-request review, shared Definition of Done, sprint demonstrations, and evidence-based acceptance integrate the workstreams.

4.1.1 Subprojects / Areas of Responsibility

- Project Management & Research Governance: research questions, protocols, baselines, metrics, validity controls, and analysis planning.

- Change Impact Analysis & Backend: Git repository integration, Git Diff extraction, AST dependency mapping, and core backend services.

- LLM & RAG Integration: source code/test indexing, vector database integration, prompt engineering, and LLM JSON output validation.

- Regression Test Selection & CI/CD: fallback mechanisms, isolated test execution environments, CI/CD pipeline integration, and automated test triggers.

- Dataset, Dashboard, and Evaluation: labeled ground truth defects, baseline execution, HTML dashboard visualization, and metric calculation (Precision, Recall, Cost).

- Quality and Documentation: all members review code and documents, maintain traceability, test their changes, and record contribution evidence.

- Steering and escalation: the Project Leader resolves routine priorities; material scope, ethics, safety, schedule, or research-validity issues are escalated to the mentor.

## Project Team

- Huy, Nguyen Tan: Project Leader, Scrum Master, and experimental-design lead.

- An, Do Ha: primary owner for change impact analysis, Git Diff parsing, and backend logic.

- Huy, Pham Phan Hoang: primary owner for RAG indexing, LLM integration, and prompt engineering.

- Khanh, Tran Hung: primary owner for regression test selection logic, fallback handling, and CI/CD integration.

- Viet, Dang Dai: primary owner for datasets, dashboard visualization, experiment execution, and evaluation analysis.

- All members: developers, testers, reviewers, document contributors, sprint participants, and backup owners as assigned in Jira.

4.2.1 Scrum Team and Responsibilities

Table 14. Scrum Team

| Full Name | Phone | Email | Position |
| --- | --- | --- | --- |
| Huy, Nguyen Tan | 0932401249 | nguyentanhuy46205@gmail.com | Project Leader / Scrum Master |
| An, Do Ha | 0815737920 | Anha0664@gmail.com | Change Impact Analysis / Backend |
| Huy, Pham Phan Hoang | 0932509973 | phamphanhoanghuy2005@gmail.com | LLM & RAG / AI Integration |
| Khanh, Tran Hung | 0783494325 | Thungkhanh19@gmail.com | Regression Test Selection / CI/CD |
| Viet, Dang Dai | 0384165721 | vdang9721@gmail.com | Dataset, Dashboard, and Evaluation |

Table 15.  Responsibilities

| Role | Responsibility | Name/Title |
| --- | --- | --- |
| Project Leader / Product Owner | Maintain product vision, approved scope, priorities, deliverable traceability, stakeholder alignment, and acceptance decisions. | Huy, Nguyen Tan |
| Scrum Master | Facilitate sprint events, capacity planning, blocker removal, risk escalation, workload review, and process improvement. | Huy, Nguyen Tan |
| Research & Integration Lead | Own evaluation protocol, baselines, budgets, CI/Docker environments, reproducibility, release controls, and analysis governance. | Huy, Nguyen Tan |
| Change Impact Analysis Lead | Own Git repository integration, Git Diff parsing, Python AST dependency mapping, and core backend services. | An, Do Ha |
| LLM & RAG Integration Lead | Own RAG indexing, vector database, LLM prompt engineering, and JSON output structure validation. | Huy, Pham Phan Hoang |
| Test Selection & CI/CD Lead | Own regression test selection logic, isolated execution environments, fallback mechanisms, and GitHub Actions workflows. | Khanh, Tran Hung |
| Dataset and Evaluation Lead | Own the 50-commit-pair ground truth dataset, baseline comparison experiments, metric calculation, and the HTML evaluation dashboard. | Viet, Dang Dai |
| Developer / Tester / Reviewer | Implement assigned work, write and execute tests, review pull requests and documents, fix defects, and maintain acceptance evidence. | All members |
| Secretary / Configuration Contributor | Rotate meeting minutes, decision records, contribution evidence, version updates, and document repositories. | All members (rotating) |
| Mentor | Review project direction, research rigor, progress, major changes, risks, validity concerns, and formal deliverables. | Jan Samuelsson |

# COMMUNICATION & REPORTING

## Communication methodology

Table 16. Communication methodology

| Audience / Attendees | Topic / Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| All team members | Daily progress, next action, blockers, and capacity changes | Each working day | Asynchronous Jira/Zalo update |
| All team members | Task coordination, integration, risks, and decisions | Twice weekly | Online or face-to-face meeting |
| Project team and mentor | Progress, research rigor, scope, risks, and deliverable review | Weekly or as agreed | Meeting and shared documents |
| Project team | Sprint planning, review, and retrospective | At each sprint boundary | Jira, demonstration, and meeting minutes |
| Relevant owner and Project Leader | Critical blocker, safety issue, major defect, or scope/validity change | As required within 24 hours | Jira issue plus direct message/call |

## Communication and report

Table 17. Communication and report

| Type of Communication | Methods / Tools | Frequency | Information | People |
| --- | --- | --- | --- | --- |
| Team Coordination and Governance |  |  |  |  |
| Daily asynchronous stand-up | Jira and Zalo | Working days | Completed work, next task, blocker, capacity change, and requested support. | All members |
| Team synchronization | Face-to-face or Zoom | Twice weekly, 20-30 minutes | Dependencies, integration status, risks, defects, and decisions requiring coordination. | All members |
| Sprint Planning | Jira and meeting | Start of each sprint | Sprint goal, selected backlog, estimates, capacity, owners, dependencies, acceptance evidence, and risks. | Project team |
| Sprint Review | Demonstration and shared evidence | End of each sprint | Completed increment, metrics, accepted/rejected work, deliverable status, and mentor feedback. | Project team; mentor when available |
| Sprint Retrospective | Meeting minutes | End of each sprint | Estimation accuracy, workload, technical gaps, defects, process issues, and improvement actions. | Project team |
| Mentor Progress Review | Meeting, email, and shared documents | Weekly or as agreed | Research method, progress, schedule, risks, validity threats, scope decisions, and document feedback. | Mentor and project team |
| Issue and Risk Escalation | Jira plus direct contact | Within 24 hours for critical issues | Impact, evidence, options, owner, mitigation, decision deadline, and required approval. | Affected owner; Project Leader; mentor if material |
| Formal Status and Evidence Report | GitHub, Jira, and Google Drive | At sprint close and milestones | Backlog status, contribution evidence, test results, experiment artifacts, decisions, risks, and deliverable versions. | Project team, mentor, and reviewers |

# CONFIGURATION MANAGEMENT

- Configuration items: source code, documentation, LLM prompt templates, datasets, experiment configurations, analysis scripts, CI workflows, Docker files, evidence, and release artifacts.

- Repository and branching: use a protected main branch, short-lived feature branches, issue-linked pull requests, at least one peer approval, and successful lint, test, and build checks before merge.

- Change control: changes to approved scope, interfaces, metrics, baselines, dataset labels, or milestone dates require an issue containing rationale, impact, owner, reviewer, and affected documents.

- Versioning and releases: use semantic versioning for the prototype, document versions for formal submissions, immutable release tags, and release notes that identify compatible datasets and configurations.

- Environment and evidence: pin dependencies through lockfiles (e.g., requirements.txt) and container definitions; retain run manifests, environment versions, LLM parameters, logs, metrics, and report outputs for accepted experiments.

- Security and recovery: protect repository access, exclude credentials (e.g., LLM API keys) and production endpoints, redact sensitive source code payloads, maintain remote backups, and verify that another member can reproduce setup from the runbook.

REFERENCES

| No. | Reference Item | Issued Date | Source | Note |
| --- | --- | --- | --- | --- |
| 1 | C1SE.26 Project Proposal Document, Version 1.4 | 8 Oct. 2026 | SmartRegression AI Team | Primary project baseline |
| 2 | Capstone Project Plan Template and Example | 10 Sep. 2026 | International School, Duy Tan University | Required structure |

DEFINITIONS AND ACRONYMS

| Acronym | Definition | Note |
| --- | --- | --- |
| API | Application Programming Interface | External REST integration |
| AST | Abstract Syntax Tree | Used for mapping code dependencies. |
| CI/CD | Continuous Integration / Continuous Delivery | Automated build, test, and release |
| CLI | Command-Line Interface | Primary local execution interface |
| CM | Configuration Management | Control of versions and changes |
| DoD | Definition of Done | Acceptance gate for work items |
| DSR | Design Science Research | Build-and-evaluate research method |
| FR | Functional Requirement | Required system behavior |
| HTTP | Hypertext Transfer Protocol | Third-party API transport |
| JSON | JavaScript Object Notation | Supported response format |
| LLM | Large Language Model | Utilized for impact reasoning and test selection. |
| MVP | Minimum Viable Product | Approved twelve-week implementation scope |
| NFR | Non-Functional Requirement | Quality or operational requirement |
| P / I / E | Probability / Impact / Exposure | Risk exposure E = P x I |
| QA | Quality Assurance | Verification and quality-control activities |
| RAG | Retrieval-Augmented Generation | Enhances AI reasoning with source code and tests. |
| REST | Representational State Transfer | Supported API style |
| RQ | Research Question | Question evaluated empirically |
| SUT | System Under Test | Application subjected to experiments |
| Vector DB | Vector Database | Supports fast context retrieval (e.g., FAISS, ChromaDB). |